## Change Log
版本 Version | 时间 Date | 作者 Author | 修改内容 Description of Changes | 备注 Remarks
1 | 2015-09-07 | 倪茜 Ni Qian | 首次发布Initial Issue

## IT项目分级标准
IT项目分级标准
IT Project Classification Standard
说明： 1、本分级标准用于在IT应用更改申请阶段和IT请求评估阶段，进行统一的分级定义和判断，以便合理调配和整合IT资源，提高IT项目管理效率； 2、IT项目级别是通过评估7项影响因素的权重得分汇总来确定； 3、本表格在填写时，根据具体情况，选择白色底色的单元格下拉选项，表格自动将得分统计在“得分”列的相应单元格中，并根据总分，自动匹配项目分类； 4、本标准适用于上海延锋江森座椅有限公司，包括所属全资分公司子公司；合资公司可参照执行。
影响 | 非常低 | 低 | 中 | 高 | 非常高 | 得分
影响的权重 | 0 | 0.5 | 1 | 2 | 3
1, 被变更的应用或系统的个数 | 0 | 1-2 | 3-4 | 5-6 | > 6 | 0
| No | No | No | No | No
2, 预估的人天数 | (0,3] | (3,10] | (10,130] | (130,260] | (260,∞) | 0
| No | No | No | No | No
3, 技术 | 1, 使用公司内已经在用的技术 2, YFJC内部IT完成（包括使用驻场的第三方工程师） 3, 对现有应用或系统的更新 | 1, 使用公司内已经在用的技术 2, YFJC内部IT完成（包括使用驻场的第三方工程师） 3, 在现有应用或系统上有小规模的功能增加 4, 需要在现有的基础上增加基础设施能力（不是必须项） | 1, 使用公司内已经在用的技术 2, YFJC内部IT或外部实施方或混合方式完成 3, 在现有应用或系统上有中等规模的功能增加 4, 需要在现有的基础上增加基础设施能力（不是必须项） | 1, 使用新技术，用来替代现有的应用或系统 （如Win7升级） | 1, 使用新技术，且是新的应用或系统 | 0
| No | No | No | No | No
4, 业务流程 | 对现有业务流程无变动 | 对现有业务流程有小幅度变更 | 在某一个业务领域中，对现有业务流程有中等幅度的变更 | 在多个业务领域中，对现有业务流程有重大的变更 | 在全公司范围内，对现有业务流程有重的变更 | 0
| No | No | No | No | No
5, 预估的项目金额 | [0,1万] | (1万,10万] | (10万,90万] | (90万,200万] | (200万,∞) - 自动归为大型项目 | 0
| No | No | No | No | No
6, 是否含有接口修改 | 如果1-5项的分值落在“服务请求”或“工作单”范围内，但要求修改接口，则增加2分，进入到“小型项目”分类 |  |  |  |  | 0
No
7, 是否需要项目经理 | 如果1-6项的分值落在“服务请求”或“工作单”范围内，但要求配专职备项目经理，则增加2分，进入到“小型项目”分类 |  |  |  |  | 0
No
项目分类 | 上限值 | 下限值 |  |  | 总分： | 0
服务请求 (Service Request) | 0 | 0
工作单 (Work Order) | 0.5 | 2
小型项目 (Minor Project) | 2.5 | 4
中型项目 (Moderate Project) | 4.5 | 8
大型项目 (Major Project) | 8.5 | 15

## IT Project Classification
IT项目分级标准
IT Project Classification Standard
Instruction： 1、This classification standard is used to define and evaluate the project classification, in the IT application change request and IT requests evaluation phase, in order to allocate and integrate resources legitimately and improve the efficiency of IT project management. 2、The classification of IT project is determined by the score which is evaluated by the 7 factors. 3、When filling in this form, choose white color cell dropdown options, form automatically scoring statistics in "score" column, and according to the total score to match project classification. 4、This standard applies to Shanghai Yanfeng Johnson Controls Seating Co., Ltd, wholly owned branches and subsidiaries, and JVs whose applications were managed by YFJC Centrally.
Impact | Very Low | Low | Medium | High | Very High | Score
Weight | 0 | 0.5 | 1 | 2 | 3
1, # of impacted systems/applications | 0 | 1-2 | 3-4 | 5-6 | > 6 | 0
| No | No | No | No | No
2, Estimated efforts (Man*Day) | (0,3] | (3,10] | (10,130] | (130,260] | (260,∞) | 0
| No | No | No | No | No
3, Technology | 1, Technology existing and supported by YFJC 2, YFJC in-house resources (includes use of outsourced partners) 3, Update to existing solution | 1, Technology existing and supported by YFJC 2, YFJC in-house resources (includes use of outsourced partners) 3, adding/changing minor functionalities to existing solution 4, Additional infrastructure capacity (not necessary) | 1, Technology existing and supported by YFJC 2, YFJC in-house resources or external resources 3, Additional moderate application functionalities 4, Additional infrastructure capacity (not necessary) | 1, New technology to YFJC, to replace current systems/applications | 1, New technology, and new systems/applications to YFJC | 0
| No | No | No | No | No
4, Business process | No changes to current business process | Minor changes to current business process | Moderate changes to current business process to one business area | Major changes to current business process, impacting multiple business areas | Major changes to current business process, impacting globally or more than one region | 0
| No | No | No | No | No
5, Estimated costs (RMB) | [0,10K] | (10K,100K] | (100K,900K] | (900K,2M] | (2M,∞) - Must be Major Project | 0
| No | No | No | No | No
6, If interface change required | If yes, at least to "Minor Project" category. |  |  |  |  | 0
No
7, If a project manager required | If yes, at least to "Minor Project" category. |  |  |  |  | 0
No
Project Category | Score Scope |  |  |  | Total Score: | 0
Service Request | 0 | 0
Work Order | 0.5 | 2
Minor Project | 2.5 | 4
Moderate Project | 4.5 | 8
Major Project | 8.5 | 15