## KW01
Module | Resp. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Unit tested by End User | Completed
FI | 刘书文 | 37 | IF(Interface) | 23 | 1 | 5 | 6 | 3 | 8
|  |  | RP(Report) | 11 | 5 |  | 4 | 2
|  |  | EH(Enhancement) | 3 |  |  |  |  | 3
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 6 |  | 1
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 28 | IF(Interface) | 10 | 2 | 1 | 1 | 2 | 4
|  |  | RP(Report) | 7 | 7
|  |  | EH(Enhancement) | 11 | 3 |  | 2 | 3 |  | 3
PP | 支志兵 | 35 | IF(Interface) | 13 | 6 | 0 | 1 | 3 | 3
|  |  | RP(Report) | 5 | 5
|  |  | EH(Enhancement) | 17 | 1 | 0 | 8 | 2 | 3 | 3
MM | 顾乐斌 | 42 | IF(Interface) | 29 | 19 | 4 | 1 | 5 |  |  |  |  | 6
|  |  | RP(Report) | 9 | 8 | 1
|  |  | EH(Enhancement) | 4 | 3 |  |  | 1 |  |  |  |  | 1
PM | 刘书文 | 23 | IF(Interface) | 18 |  | 4 | 1 | 13
|  |  | RP(Report) | 5 |  | 5
|  |  | EH(Enhancement) | 0
SUM |  | 173 |  | 173 | 67 | 20 | 25 | 34 | 21 | 6 | 0 | 0
|  |  | IF(Interface) | 93 | 38.73% | 11.56% | 14.45% | 19.65% | 12.14% | 3.468% | 0% | 0%
|  |  | RP(Report) | 44
|  |  | EH(Enhancement) | 36
Note on N14: 外围系统间的接口
Note on N16: 删除标记

## KW02
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Unit tested by End User | Completed |  |  | Sub-total
FI | 刘书文 | 37 | IF(Interface) | 23 | 1 | 5 |  |  | 17 |  |  |  |  | IF(Interface) | 92
|  |  | RP(Report) | 6 | 1 |  | 4 | 1 | [5 empty] | RP(Report) | 42
|  |  | EH(Enhancement) | 8 | 2 |  | 2 | 1 | 3 |  |  |  |  | EH(Enhancement) | 42
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 28 | IF(Interface) | 10 |  |  | 2 | 1 | 7
|  |  | RP(Report) | 7 | 5 | 1 | 1
|  |  | EH(Enhancement) | 11 | 1 | 2 |  | 4 | 4
PP | 支志兵 | 35 | IF(Interface) | 13 | 3 | 1 | 1 | 4 | 4
|  |  | RP(Report) | 5 | 5
|  |  | EH(Enhancement) | 17 | 1 |  | 3 | 5 | 8
MM | 顾乐斌 | 44 | IF(Interface) | 27 | 10 |  | 7 | 4 | 6 |  |  |  | 本周取消2个接口MM_IF_005A,MM_IF_005B,采购计划
|  |  | RP(Report) | 12 | 11 | 1
|  |  | EH(Enhancement) | 5 | 4 |  |  | 1 |  |  |  |  | 本周取消1个开发FC-MM-006维护销售物流运费结算方案
PM | 刘书文 | 23 | IF(Interface) | 18 |  | 2 | 1 | 15
|  |  | RP(Report) | 5 | 2 | 2 | 1
|  |  | EH(Enhancement) | 0
GRC | 严达 | 1 | IF(Interface) | 1 | 1
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 176 |  | 176 | 51 | 16 | 24 | 36 | 49 | 0 | 0 | 0
Record Date：2016/1/13 |  |  | Rate： |  | 28.98% | 9.091% | 13.64% | 20.45% | 27.84% | 0% | 0% | 0%

## KW03
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FI | 刘书文 | 36 | IF(Interface) | 19 | 1 |  | 1 |  | 16 |  |  |  |  | 1 | IF(Interface) | 97
|  |  | RP(Report) | 9 | 4 |  | 4 |  | 1 | [5 empty] | RP(Report) | 43
|  |  | EH(Enhancement) | 8 | 2 |  | 2 | 1 | 3 | [5 empty] | EH(Enhancement) | 44
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  | 2 | 10 | [5 empty] | 增加两个接口，但都由PI进行分发
|  |  | RP(Report) | 7 | 5 | 1 | 1
|  |  | EH(Enhancement) | 11 | 1 | 2 |  |  | 4 | 4
PP | 支志兵 | 41 | IF(Interface) | 19 | 6 |  | 1 | 3 | 5 | 4 |  |  |  |  | 对同一接口分发到多个系统进行了拆分，NO-Start为EDI
|  |  | RP(Report) | 5 | 5
|  |  | EH(Enhancement) | 17 | 1 |  | 1 | 2 | 9 | 4
MM | 顾乐斌 | 48 | IF(Interface) | 29 | 7 |  | 4 | 5 | 11 |  |  |  |  | 2
|  |  | RP(Report) | 12 | 10 | 1 |  | 1
|  |  | EH(Enhancement) | 7 | 5 |  |  |  | 1 |  |  |  |  | 1
PM | 刘书文 | 21 | IF(Interface) | 18 |  |  |  | 5 | 13
|  |  | RP(Report) | 3 |  |  | 3 | [7 empty] | PM_RP_001放入MM模块开发
|  |  | EH(Enhancement) | 0 | [10 empty] | PM_RP_002由MES开发
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 184 |  | 184 | 51 | 6 | 19 | 19 | 73 | 12 | 0 | 0 | 0 | 4
Record Date：2016/1/20 |  |  | Rate： |  | 27.72% | 3.261% | 10.33% | 10.33% | 39.67% | 6.522% | 0% | 0% | 0% | 2.174%
Note on F11: Zhi Zhibing(YFPOSAP): 同一接口分发到多个系统进行了拆分，未开始项为EDI系统，部分为二期项目

## KW04
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FI | 刘书文 | 37 | IF(Interface) | 19 | 1 |  | 1 |  | 16 |  |  |  |  | 1 | IF(Interface) | 97
|  |  | RP(Report) | 9 | 1 |  | 4 | 3 | 1 | [5 empty] | RP(Report) | 43
|  |  | EH(Enhancement) | 9 | 1 |  | 2 | 3 | 3 | [5 empty] | EH(Enhancement) | 46
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  | 2 | 10
|  |  | RP(Report) | 7 | 5 | 1 | 1
|  |  | EH(Enhancement) | 11 | 1 |  | 2 |  | 4 | 4
PP | 支志兵 | 41 | IF(Interface) | 19 | 6 |  | 1 | 3 | 5 | 4
|  |  | RP(Report) | 5 | 3 |  | 2
|  |  | EH(Enhancement) | 17 | 1 |  | 1 | 1 | 10 | 4
MM | 顾乐斌 | 49 | IF(Interface) | 29 | 3 | 4 | 2 | 4 | 14 |  |  |  |  | 2
|  |  | RP(Report) | 12 | 10 | 1 |  | 1
|  |  | EH(Enhancement) | 8 | 4 |  | 1 |  | 2 |  |  |  |  | 1
PM | 刘书文 | 21 | IF(Interface) | 18 |  |  |  | 3 | 15
|  |  | RP(Report) | 3 |  | 1 | 2
|  |  | EH(Enhancement) | 0
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 186 |  | 186 | 40 | 9 | 21 | 20 | 80 | 12 | 0 | 0 | 0 | 4
Record Date：2016/1/27 |  |  | Rate： |  | 21.51% | 4.839% | 11.29% | 10.75% | 43.01% | 6.452% | 0% | 0% | 0% | 2.151%
Note on F11: Zhi Zhibing(YFPOSAP): 同一接口分发到多个系统进行了拆分，未开始项为EDI系统，部分为二期项目

## KW05
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 41 | IF(Interface) | 21 |  |  | 3 |  | 17 |  |  |  |  | 1 |  | IF(Interface) | 102
|  |  | RP(Report) | 9 | 1 |  | 4 |  | 4 | [6 empty] | RP(Report) | 43
|  |  | EH(Enhancement) | 11 | 1 |  | 4 |  | 6 | [6 empty] | EH(Enhancement) | 49
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  |  | 12
|  |  | RP(Report) | 7 | 5 |  | 2
|  |  | EH(Enhancement) | 11 | 1 |  | 2 |  | 4 | 4
PP | 支志兵 | 41 | IF(Interface) | 19 | 0 |  | 3 | 2 | 7 | 4 |  |  |  | 3 | 将二期EDI删除
|  |  | RP(Report) | 5 | 2 |  | 3
|  |  | EH(Enhancement) | 17 | 1 |  | 1 |  | 11 | 4
MM | 顾乐斌 | 48 | IF(Interface) | 27 | 3 | 3 |  | 4 | 7 | 10
|  |  | RP(Report) | 12 | 10 | 1 |  | 1
|  |  | EH(Enhancement) | 9 | 7 |  |  |  |  | 2
PM | 刘书文 | 21 | IF(Interface) | 18 |  |  |  | 1 | 17
|  |  | RP(Report) | 3 |  | 1 | 2
|  |  | EH(Enhancement) | 0
GRC | 严达 | 5 | IF(Interface) | 5 | 1 |  |  |  | 4
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 194 |  | 194 | 36 | 7 | 26 | 8 | 89 | 24 | 0 | 0 | 0 | 4
Record Date：2016/2/3 |  |  | Rate： |  | 18.56% | 3.608% | 13.4% | 4.124% | 45.88% | 12.37% | 0% | 0% | 0% | 2.062%
Note on F11: Zhi Zhibing(YFPOSAP): 同一接口分发到多个系统进行了拆分，未开始项为EDI系统，部分为二期项目

## KW07
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FI | 刘书文 | 0 | IF(Interface) | 0 | [10 empty] | IF(Interface) | 28
|  |  | RP(Report) | 0 | [10 empty] | RP(Report) | 12
|  |  | EH(Enhancement) | 0 | [10 empty] | EH(Enhancement) | 28
CO | 刘书文 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  |  | 12
|  |  | RP(Report) | 7 | 5 |  | 2
|  |  | EH(Enhancement) | 11 | 1 |  | 2 |  | 4 | 4
PP | 支志兵 | 38 | IF(Interface) | 16 | 0 |  | 3 | 1 | 8 | 4
|  |  | RP(Report) | 5 | 1 |  | 3 | 1
|  |  | EH(Enhancement) | 17 | 1 |  | 1 |  | 11 | 4
MM | 顾乐斌 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
PM | 刘书文 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 68 |  | 68 | 8 | 0 | 11 | 2 | 35 | 12 | 0 | 0 | 0 | 0
Record Date：2016/2/17 |  |  | Rate： |  | 11.76% | 0% | 16.18% | 2.941% | 51.47% | 17.65% | 0% | 0% | 0% | 0%
Note on F11: Zhi Zhibing(YFPOSAP): 同一接口分发到多个系统进行了拆分，未开始项为EDI系统，部分为二期项目

## KW08
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FI | 刘书文 | 40 | IF(Interface) | 20 |  |  |  | 3 | 17 | [5 empty] | IF(Interface) | 98
|  |  | RP(Report) | 9 | 1 |  | 1 |  | 7 | [5 empty] | RP(Report) | 43
|  |  | EH(Enhancement) | 11 | 1 |  | 1 |  | 9 | [5 empty] | EH(Enhancement) | 48
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  |  | 12
|  |  | RP(Report) | 7 | 5 |  |  | 2
|  |  | EH(Enhancement) | 11 | 1 | 0 | 2 |  | 8
PP | 支志兵 | 38 | IF(Interface) | 16 | 0 |  | 2 | 2 | 12
|  |  | RP(Report) | 5 | 1 |  | 2 | 2
|  |  | EH(Enhancement) | 17 | 1 |  |  |  | 16
MM | 顾乐斌 | 46 | IF(Interface) | 27 | 3 |  | 3 | 2 | 10 | 9
|  |  | RP(Report) | 12 | 9 | 1 |  | 2
|  |  | EH(Enhancement) | 7 | 5 |  |  |  |  | 2
PM | 刘书文 | 21 | IF(Interface) | 18 |  |  |  |  | 18
|  |  | RP(Report) | 3 |  |  |  | 2 | 1
|  |  | EH(Enhancement) | 0
GRC | 严达 | 6 | IF(Interface) | 5 | 0 | 0 | 0 | 0 | 5
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
SUM |  | 189 |  | 189 | 31 | 3 | 13 | 15 | 116 | 11 | 0 | 0 | 0 | 0
Record Date：2016/2/24 |  |  | Rate： |  | 16.4% | 1.587% | 6.878% | 7.937% | 61.38% | 5.82% | 0% | 0% | 0% | 0%

## KW09
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total | YFPO SAP Project Interface Summary
FI | 刘书文 | 40 | IF(Interface) | 20 |  |  |  |  | 20 | [6 empty] | IF(Interface) | 99 |  |  |  | SAP | [5 empty] | Total
|  |  | RP(Report) | 9 | 1 |  |  | 1 | 7 | [6 empty] | RP(Report) | 43 |  |  |  | FICO | PM | MM | PP | SD | GRC
|  |  | EH(Enhancement) | 11 | 1 |  | 1 |  | 9 | [6 empty] | EH(Enhancement) | 50 | Surrounding System | 1 | QAD | 1 | [5 empty] | 1
CO | 刘书文 | 8 | IF(Interface) | 0 | [14 empty] | 2 | FND | 6 |  |  |  | 1 |  | 7
|  |  | RP(Report) | 7 | 3 | 2 | 2 | [11 empty] | 3 | HFM | 3 | [5 empty] | 3
|  |  | EH(Enhancement) | 1 | 1 | [13 empty] | 4 | WFM | 10 | 8 | 9 | 2 | 4 | 5 | 38
SD | 支志兵 | 30 | IF(Interface) | 12 |  |  |  | 2 | 10 | [9 empty] | 5 | IPUR |  |  | 3 |  |  |  | 3
|  |  | RP(Report) | 7 | 5 |  |  |  | 2 | [9 empty] | 6 | HRM |  |  | 1 |  |  |  | 1
|  |  | EH(Enhancement) | 11 | 1 | 0 | 2 |  | 4 | 4 | [8 empty] | 7 | IBOM |  |  |  | 1 |  |  | 1
PP | 支志兵 | 39 | IF(Interface) | 16 | 0 |  | 1 | 3 | 5 | 7 | [8 empty] | 8 | MES |  | 9 | 8 | 9 | 3 |  | 29
|  |  | RP(Report) | 5 | 1 |  | 2 | 1 | 1 | [9 empty] | 9 | ISV |  |  | 6 | 1 |  |  | 7
|  |  | EH(Enhancement) | 18 | 2 |  |  |  | 8 | 8 |  |  |  |  | 增加PP_UL_025 |  |  |  | 10 | PUS |  |  |  |  | 4 |  | 4
MM | 顾乐斌 | 45 | IF(Interface) | 27 | 2 |  |  | 1 | 9 | 15 | [8 empty] | 11 | PDA |  | 2 |  |  |  |  | 2
|  |  | RP(Report) | 11 | 10 |  |  |  | 1 | [9 empty] | 12 | EDI |  |  |  | 3 |  |  | 3
|  |  | EH(Enhancement) | 7 | 3 |  |  |  | 4 | [8 empty] | Total |  |  | 20 | 19 | 27 | 16 | 12 | 5 | 99
PM | 刘书文 | 24 | IF(Interface) | 19 |  |  |  |  | 16 | 3
|  |  | RP(Report) | 4 |  | 1 |  |  | 3
|  |  | EH(Enhancement) | 1 |  |  |  | 1
GRC | 严达 | 6 | IF(Interface) | 5 |  |  |  |  | 5
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
SUM |  | 192 |  | 192 | 30 | 3 | 8 | 9 | 105 | 37 | 0 | 0 | 0 | 0
Record Date：2016/3/2 |  |  | Rate： |  | 15.62% | 1.562% | 4.167% | 4.688% | 54.69% | 19.27% | 0% | 0% | 0% | 0%

## KW10
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 41 | IF(Interface) | 20 |  |  |  |  | 11 | 9 | [5 empty] | IF(Interface) | 100
|  |  | RP(Report) | 9 | 1 |  |  | 1 | 7 | [6 empty] | RP(Report) | 45
|  |  | EH(Enhancement) | 12 | 1 | 1 |  |  | 10 | [5 empty] | 新增一个 | EH(Enhancement) | 52
CO | 刘书文 | 8 | IF(Interface) | 0
|  |  | RP(Report) | 7 | 3 | 2 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 33 | IF(Interface) | 13 |  |  |  | 2 | 11
|  |  | RP(Report) | 8 | 6 |  |  |  | 2
|  |  | EH(Enhancement) | 12 | 1 |  | 3 |  | 4 | 4
PP | 支志兵 | 40 | IF(Interface) | 16 |  |  | 1 | 3 | 5 | 7
|  |  | RP(Report) | 5 | 2 |  | 1 | 1 | 1
|  |  | EH(Enhancement) | 19 | 3 |  |  |  | 8 | 8
MM | 顾乐斌 | 45 | IF(Interface) | 27 | 2 |  |  | 2 | 9 | 14
|  |  | RP(Report) | 12 | 9 | 1 |  |  | 2
|  |  | EH(Enhancement) | 6 | 2 | 1 |  |  | 2 | 1
PM | 刘书文 | 24 | IF(Interface) | 19 |  |  |  |  | 16 | 3
|  |  | RP(Report) | 4 |  | 1 |  |  | 3
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
GRC | 严达 | 6 | IF(Interface) | 5 |  |  |  |  | 5
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
SUM |  | 197 |  | 197 | 31 | 6 | 7 | 9 | 98 | 46 | 0 | 0 | 0 | 0
Record Date：2016/3/9 |  |  | Rate： |  | 15.74% | 3.046% | 3.553% | 4.569% | 49.75% | 23.35% | 0% | 0% | 0% | 0%

## KW11
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 43 | IF(Interface) | 22 |  |  |  |  | 3 |  | 19 |  |  |  | 新增两个 | IF(Interface) | 104
|  |  | RP(Report) | 9 | 1 |  |  |  | 4 | 4 | [5 empty] | RP(Report) | 45
|  |  | EH(Enhancement) | 12 |  |  | 2 |  |  | 10 | [5 empty] | EH(Enhancement) | 52
CO | 刘书文 | 7 | IF(Interface) | 0
|  |  | RP(Report) | 6 | 4 |  |  | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 37 | IF(Interface) | 16 |  |  |  | 1 | 11 |  |  |  |  | 4 | 累计取消四个
|  |  | RP(Report) | 9 | 7 |  |  |  | 2
|  |  | EH(Enhancement) | 12 | 1 |  | 3 |  | 4 | 4
PP | 支志兵 | 40 | IF(Interface) | 16 |  |  |  | 3 | 6 | 7 |  |  |  |  | 开发为EDI调整后的程序开发
|  |  | RP(Report) | 5 | 1 |  | 1 | 1 | 2
|  |  | EH(Enhancement) | 19 | 3 |  |  |  | 8 | 8
MM | 顾乐斌 | 45 | IF(Interface) | 27 | 2 |  |  | 2 | 9 | 14
|  |  | RP(Report) | 12 | 9 | 1 |  |  | 2
|  |  | EH(Enhancement) | 6 | 2 | 1 |  |  | 2 | 1
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 7 | 11
|  |  | RP(Report) | 4 |  |  |  |  | 4
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
GRC | 严达 | 6 | IF(Interface) | 5 | [6 empty] | 5
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 1 | [6 empty] | 1
SUM |  | 201 |  | 201 | 31 | 2 | 6 | 9 | 65 | 59 | 25 | 0 | 0 | 4
Record Date：2016/3/16 |  |  | Rate： |  | 15.42% | 0.995% | 2.985% | 4.478% | 32.34% | 29.35% | 12.44% | 0% | 0% | 1.99%

## KW12
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 43 | IF(Interface) | 22 |  |  |  |  | 3 |  | 17 | 2 |  |  | 新增两个 | IF(Interface) | 98
|  |  | RP(Report) | 9 | 1 |  |  |  | 4 | 4 | [5 empty] | RP(Report) | 46
|  |  | EH(Enhancement) | 12 |  |  | 2 |  |  | 10 | [5 empty] | EH(Enhancement) | 53
CO | 刘书文 | 7 | IF(Interface) | 0
|  |  | RP(Report) | 6 | 4 |  |  | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 36 | IF(Interface) | 15 |  |  |  |  | 5 |  | 6 |  |  | 4 | 累计取消四个
|  |  | RP(Report) | 9 | 5 |  | 2 | 1 | 1
|  |  | EH(Enhancement) | 12 | 1 |  |  | 2 | 2 | 6 |  |  |  | 1
PP | 支志兵 | 42 | IF(Interface) | 16 |  |  |  |  | 7 | 2 | 7 |  |  |  | 开发为EDI调整后的程序开发
|  |  | RP(Report) | 5 |  |  |  | 1 | 3 |  |  |  |  | 1
|  |  | EH(Enhancement) | 21 | 1 |  | 4 |  | 8 | 8
MM | 顾乐斌 | 46 | IF(Interface) | 27 | 2 |  |  | 2 | 9 | 14
|  |  | RP(Report) | 13 | 9 | 2 |  |  | 2
|  |  | EH(Enhancement) | 6 | 2 | 1 |  |  | 2 | 1
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 16
|  |  | RP(Report) | 4 |  |  |  |  | 4
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 197 |  | 197 | 26 | 3 | 8 | 8 | 53 | 45 | 46 | 2 | 0 | 6
Record Date：2016/3/16 |  |  | Rate： |  | 13.2% | 1.523% | 4.061% | 4.061% | 26.9% | 22.84% | 23.35% | 1.015% | 0% | 3.046%

## KW13
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FI | 刘书文 | 45 | IF(Interface) | 24 |  |  |  | 2 | 2 | 1 | 7 | 12 |  |  | IF(Interface) | 95
|  |  | RP(Report) | 9 | 1 |  |  |  | 4 | 4 |  |  |  |  | RP(Report) | 44
|  |  | EH(Enhancement) | 12 |  |  | 1 |  | 1 | 10 |  |  |  |  | EH(Enhancement) | 57
CO | 刘书文 | 7 | IF(Interface) | 0
|  |  | RP(Report) | 6 | 4 |  |  | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 33 | IF(Interface) | 12 |  |  |  |  | 6 | 6
|  |  | RP(Report) | 9 | 5 |  | 2 |  | 2
|  |  | EH(Enhancement) | 12 | 1 |  |  |  | 4 | 6 | 1
PP | 支志兵 | 41 | IF(Interface) | 16 |  |  |  |  | 7 | 2 | 7
|  |  | RP(Report) | 4 |  |  |  | 1 | 3
|  |  | EH(Enhancement) | 21 | 1 |  | 3 |  | 9 | 8
MM | 顾乐斌 | 47 | IF(Interface) | 25 |  |  |  | 1 | 5 | 15 | 4
|  |  | RP(Report) | 12 | 8 | 2 |  |  | 1 | 1
|  |  | EH(Enhancement) | 10 |  |  |  | 1 | 3 | 6
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 16
|  |  | RP(Report) | 4 |  |  |  |  | 4
|  |  | EH(Enhancement) | 1 |  |  |  |  | 1
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 196 |  | 196 | 21 | 2 | 6 | 7 | 54 | 59 | 35 | 12 | 0 | 0
Record Date：2016/3/16 |  |  | Rate： |  | 10.71% | 1.02% | 3.061% | 3.571% | 27.55% | 30.1% | 17.86% | 6.122% | 0% | 0%

## KW14
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 45 | IF(Interface) | 24 | [6 empty] | 10 | 14 |  |  |  | IF(Interface) | 98
|  |  | RP(Report) | 9 | 1 |  |  |  | 4 | 4 | [5 empty] | RP(Report) | 44
|  |  | EH(Enhancement) | 12 |  |  | 1 |  | 1 | 10 | [5 empty] | EH(Enhancement) | 61
CO | 刘书文 | 7 | IF(Interface) | 0
|  |  | RP(Report) | 6 | 1 | 2 | 1 | 2
|  |  | EH(Enhancement) | 1 | 1
SD | 支志兵 | 36 | IF(Interface) | 13 |  |  |  | 1 | 6 | 6
|  |  | RP(Report) | 10 | 3 |  | 1 | 2 | 3 | 1
|  |  | EH(Enhancement) | 13 |  |  |  |  | 4 | 6 |  |  | 1 | 2 | 完成项销售定价增强
PP | 支志兵 | 43 | IF(Interface) | 16 |  |  |  |  | 7 | 2 | 7
|  |  | RP(Report) | 4 |  |  |  |  | 4
|  |  | EH(Enhancement) | 23 | 2 |  | 2 |  | 10 | 7 |  |  | 1 | 1 | 完成项为增加PM的四个字段
MM | 严达 | 49 | IF(Interface) | 27 | 2 |  |  | 1 | 5 | 15 | 4
|  |  | RP(Report) | 12 | 8 | 2 |  |  | 1 | 1
|  |  | EH(Enhancement) | 10 |  |  |  | 1 | 3 | 6
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 16
|  |  | RP(Report) | 3 |  |  |  |  | 2 |  |  | 1
|  |  | EH(Enhancement) | 2 |  |  |  |  | 2
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 203 |  | 203 | 18 | 4 | 5 | 7 | 54 | 58 | 37 | 15 | 2 | 3
Record Date：2016/3/16 |  |  | Rate： |  | 8.867% | 1.97% | 2.463% | 3.448% | 26.6% | 28.57% | 18.23% | 7.389% | 0.9852% | 1.478%

## KW15
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 45 | IF(Interface) | 24 | [6 empty] | 5 | 19 |  |  |  | IF(Interface) | 105
|  |  | RP(Report) | 9 | 1 |  |  |  | 4 | 4 | [5 empty] | RP(Report) | 47
|  |  | EH(Enhancement) | 12 |  |  | 1 |  | 1 | 10 | [5 empty] | EH(Enhancement) | 61
CO | 刘书文 | 12 | IF(Interface) | 0
|  |  | RP(Report) | 8 | 4 | 1 | 1 | 2
|  |  | EH(Enhancement) | 4 | 1 | 1 |  | 1 | 1
SD | 支志兵 | 34 | IF(Interface) | 13 |  |  |  |  | 2 | 1 | 10
|  |  | RP(Report) | 10 | 3 |  | 1 | 2 | 3 | 1
|  |  | EH(Enhancement) | 11 |  |  |  |  | 4 | 6 |  |  | 1
PP | 支志兵 | 43 | IF(Interface) | 16 |  |  |  |  | 3 | 1 | 3 |  | 9
|  |  | RP(Report) | 5 |  |  | 1 |  | 3 |  |  |  | 1
|  |  | EH(Enhancement) | 22 | 1 |  | 1 | 1 | 3 | 4 |  |  | 12
MM | 严达 | 56 | IF(Interface) | 34 | 7 | 1 | 1 | 1 | 3 | 17 | 4
|  |  | RP(Report) | 12 | 5 | 1 | 2 |  | 3 | 1
|  |  | EH(Enhancement) | 10 |  |  |  |  | 4 | 6 |  |  |  |  | ZMME001程序根据用户实际需求需做较大改动
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 15 | 1
|  |  | RP(Report) | 3 |  |  |  |  | 2 |  |  | 1
|  |  | EH(Enhancement) | 2 |  |  |  |  | 2
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 213 |  | 213 | 22 | 4 | 8 | 7 | 40 | 51 | 37 | 21 | 23 | 0
Record Date：2016/3/16 |  |  | Rate： |  | 10.33% | 1.878% | 3.756% | 3.286% | 18.78% | 23.94% | 17.37% | 9.859% | 10.8% | 0%
2

## KW16
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 44 | IF(Interface) | 23 | [7 empty] | 23 |  |  | 删除一个重复项 | IF(Interface) | 106
|  |  | RP(Report) | 9 | 1 |  |  |  |  | 5 |  | 3 |  |  |  | RP(Report) | 48
|  |  | EH(Enhancement) | 12 |  |  | 1 |  | 1 | 9 |  | 1 |  |  |  | EH(Enhancement) | 60
CO | 刘书文 | 12 | IF(Interface) | 0
|  |  | RP(Report) | 8 | 2 | 1 | 2 | 1 | 2
|  |  | EH(Enhancement) | 4 |  | 1 |  | 1 |  | 2
SD | 支志兵 | 35 | IF(Interface) | 13 |  |  |  |  | 2 | 1 | 10
|  |  | RP(Report) | 11 | 4 |  | 1 | 2 | 3 | 1 |  |  |  |  | 新增了一个对比表
|  |  | EH(Enhancement) | 11 |  |  |  |  | 4 | 6 |  |  | 1
PP | 支志兵 | 44 | IF(Interface) | 18 | 2 |  |  |  | 3 | 1 | 3 |  | 9 |  | 新增两个工时接口
|  |  | RP(Report) | 6 | 1 |  |  |  | 4 |  |  |  | 1 |  | 新增工时报表
|  |  | EH(Enhancement) | 20 |  |  | 1 |  | 4 | 3 |  |  | 12
MM | 严达 | 56 | IF(Interface) | 34 | 7 | 1 | 1 | 1 | 2 | 2 | 20
|  |  | RP(Report) | 11 | 5 | 1 | 1 |  | 3 | 1
|  |  | EH(Enhancement) | 11 |  |  | 1 |  | 1 | 2 |  | 7
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 15 | 1
|  |  | RP(Report) | 3 |  |  |  |  | 2 |  |  | 1
|  |  | EH(Enhancement) | 2 |  |  |  |  | 2
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 214 |  | 214 | 22 | 4 | 8 | 5 | 35 | 33 | 48 | 36 | 23 | 0
Record Date：2016/3/16 |  |  | Rate： |  | 10.28% | 1.869% | 3.738% | 2.336% | 16.36% | 15.42% | 22.43% | 16.82% | 10.75% | 0%
2

## KW17
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  |  | Sub-total
FI | 刘书文 | 55 | IF(Interface) | 24 | [6 empty] | 1 | 23 |  |  | 新增一个HFM主数据 | IF(Interface) | 42
|  |  | RP(Report) | 19 | 9 |  |  |  |  | 4 |  | 1 | 5 |  | 新增10张报表 | RP(Report) | 31
|  |  | EH(Enhancement) | 12 |  |  | 1 |  | 1 | 9 |  | 1 |  |  |  | EH(Enhancement) | 18
CO | 刘书文 | 13 | IF(Interface) | 0
|  |  | RP(Report) | 9 | 2 |  |  | 4 |  | 1 |  | 2
|  |  | EH(Enhancement) | 4 | [5 empty] | 1 |  | 2 | 1
SD | 支志兵 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
PP | 支志兵 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
MM | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
PM | 刘书文 | 23 | IF(Interface) | 18 |  |  |  |  | 2 |  | 15 | 1
|  |  | RP(Report) | 3 |  |  |  |  | 2 |  |  | 1
|  |  | EH(Enhancement) | 2 |  |  |  |  | 2
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 91 |  | 91 | 11 | 0 | 1 | 4 | 7 | 15 | 16 | 31 | 6 | 0
Record Date：2016/3/16 |  |  | Rate： |  | 12.09% | 0% | 1.099% | 4.396% | 7.692% | 16.48% | 17.58% | 34.07% | 6.593% | 0%
2

## KW18
Module | R. | Total | Dev. Type | Sub-total | Not Start | In FS | FS Wait for Approval | In Develop | Completed by Developer | Unit tested by Application | Integrate Tested | Unit tested by End User | Completed | Cancel |  | Sub-total
FICO | 刘书文 | 67 | IF(Interface) | 23 |  |  |  | 1 | 3 |  | 19 |  |  |  | IF(Interface) | 101
|  |  | RP(Report) | 28 | 11 |  |  | 4 |  | 5 |  | 3 | 5 |  | RP(Report) | 63
|  |  | EH(Enhancement) | 16 |  |  | 1 |  | 1 | 10 |  | 3 | 1 |  | EH(Enhancement) | 59
SD | 支志兵 | 36 | IF(Interface) | 13 |  |  |  |  | 2 | 1 | 10
|  |  | RP(Report) | 12 | 2 |  | 1 | 2 | 2 | 2 |  | 3
|  |  | EH(Enhancement) | 11 |  |  |  |  | 3 | 7 |  |  | 1
PP | 支志兵 | 44 | IF(Interface) | 18 | 2 |  |  |  | 3 | 1 | 3 |  | 9
|  |  | RP(Report) | 6 | 1 |  | 1 | 1 | 2 |  |  |  | 1
|  |  | EH(Enhancement) | 20 |  |  | 1 | 1 | 3 | 3 |  |  | 12
MM | 严达 | 49 | IF(Interface) | 27 |  |  |  |  | 3 | 2 | 20 |  | 2
|  |  | RP(Report) | 11 | 5 | 1 | 1 |  | 1 | 3
|  |  | EH(Enhancement) | 11 |  |  | 1 |  |  | 6 |  | 4
PM | 刘书文 | 27 | IF(Interface) | 20 |  |  |  | 2 |  | 2 | 10 | 4 | 2
|  |  | RP(Report) | 6 | 2 |  |  |  | 1 | 1 |  | 1 | 1
|  |  | EH(Enhancement) | 1 | [5 empty] | 1
GRC | 严达 | 0 | IF(Interface) | 0
|  |  | RP(Report) | 0
|  |  | EH(Enhancement) | 0
SUM |  | 223 |  | 223 | 23 | 1 | 6 | 11 | 24 | 44 | 62 | 18 | 34 | 0
Record Date：2016/4/27 |  |  | Rate： |  | 10.31% | 0.4484% | 2.691% | 4.933% | 10.76% | 19.73% | 27.8% | 8.072% | 15.25% | 0%