## New Program
模块 Module | 编号 Index ID | 开发功能说明书 (Function Spec) | 程序说明 Description | 事务代码/功能组 Tcode/FG | 主程序及相关程序名称(Main Prog name and relevant) | 有内部权限控制? Has internal authority control? | 所属部门 End User Department | 功能说明书负责人Function Spec Owner | 开发负责人ABAP Owner | 程序类型 Program Type | 复杂程度 Difficulty | 优先级 Priority | 开发类 Package | 功能说明所需人天Function Spec Man Days | 开发程序所需人天Development Man Days | 单元测试所需人天Unit Testing Man Days | 总体状态 Overall Status | 功能说明书开始日期 Function Spec Start date | 原型开发结束和功能说明书结束等待审核日期Prototype and Function Spec complete date | 功能说明书结束获得客户认可日期 Date on Function Spec Confirmation | 开发实际开始日期Dev Plan Start Date | 开发计划完成日期Dev Plan End Date | 开发实际完成日期Dev Actual End Date | 单元测试状态 Unit Test Status | KBU测试人员 KBU Tester | KBU测试开始日期 KBU Test Start Date | KBU测试结束日期 KBU Test Finish Date | 备注 Remark
PP | PP_EN_001 |  | 物料主数据客户化字段 Material master data customized fields | N/A |  |  | ALL | 张凯凯 | 徐志新 | Enhancement | L | H | ZPP01 | 1.5 | 2 | 1 | Complete | 2015-11-25 | 2015-11-26 |  | 2015-12-17 | 2015-12-21
PP | PP_UL_002 |  | 物料主数据导入 Material master data batch input | ZPP001 |  | Y | ALL | 张凯凯 | 王毅 | Upload | L | H | ZPP01 | 1 | 2 | 2 | Unit tested by Application | 2015-12-02 | 2015-12-03 |  | 2015-12-18 | 2015-12-22
PP | PP_UL_003 |  | 物料主数据销售视图导入 Material Master Data batch input(Sales View) | ZPP002 |  | Y | ALL | 张凯凯 | 王毅 | Upload | L | H | ZPP01 | 1 | 1 | 1 | Unit tested by Application | 2015-12-03 | 2015-12-04 |  | 2015-12-18 | 2015-12-21
PP | PP_UL_004 |  | 物料主数据分类视图导入 Material Master Data batch input | ZPP003 |  | Y | ALL | 张凯凯 | 王毅 | Upload | L | H | ZPP01 | 1 | 2 | 2 | Unit tested by Application | 2015-12-22 | 2015-12-22 |  | 2015-12-23 | 2015-12-25 | [5 empty] | 2. SAP系统内采用Y，YSL和YSR来归类扰流板。如下图。SAP导入程序中自动进行匹配转换。 DS-》Y 2 Spoiler 扰流板 DSL—》YSL 2 Side spoiler-Left 侧扰流板-左 DSR—》YSR 2 Side spoiler-Right 侧扰流板-右
PP | PP_UL_019 |  | 车型BOM主数据导入 Vehicle BOM Master Data Batch input | ZPP005 |  |  | 工厂 | 支志兵 | 曲凯 | Upload | L | H | ZPP01 | 5 | 5 | 1 | Complete | 2015-12-17 | 2015-12-24 |  | 2016-01-08 | 2016-01-15
PP | PP_UL_006 |  | BOM主数据导入（FS合并至接口文档） BOM Master Data Batch input | ZPP006 |  |  | 工厂 | 张凯凯 | 白官玺 | Upload | M | H | ZPP01 | 3 | 5 | 3 | Complete | 2015-12-30 | 2016-01-04 |  | 2016-01-11
PP | PP_FC_024 |  | W2件BOM主数据创建 Create BOM for W2 parts | ZPP039 |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | M | ZPP01 | 1 | 1 | 1 | Completed by Developer | 2016-01-05 | 2016-01-06
PP | PP_UL_007 |  | 工作中心主数据导入程序 Work center batch input | ZPP007 |  |  | 工厂 | 张凯凯 | 曲凯 | Upload | L | H | ZPP01 | 0.5 | 1 | 1 | Complete | 2015-12-09 | 2015-12-09 |  | 2015-12-22 | 2015-12-23
PP | PP_UL_008 |  | 工艺路线主数据导入程序 Routing batch input | ZPP008 |  |  | 工厂 | 张凯凯 | 曲凯 | Upload | L | H | ZPP01 | 1 | 1 | 1 | Complete | 2015-12-09 | 2015-12-10 |  | 2015-12-22 | 2015-12-23
PP | PP_UL_010 |  | 车型计划导入（年度/18周预测） Vehicle plan batch input(annual/18weeks forecast | ZPP010 |  |  | 工厂 | 邱砾佶 | 曲凯 | Upload | M | H | ZPP01 | 5 | 3 | 2 | Complete | 2015-12-16 | 2015-12-23 |  | 2015-12-30 | 2016-01-04
PP | PP_FC_011 |  | 车型计划分解（年度/18周预测） Vehicle plan disaggregation(annual/18weeks forecast) | ZPP011 |  |  | 工厂 | 张凯凯 | 曲凯 | Function | M | H | ZPP01 | 2 | 3 | 2 | Complete | 2015-12-17 | 2015-12-21 |  | 2015-01-04 | 2015-01-07
PP | PP_FC_012 |  | 车型计划传输（年度/18周预测） Transfer vehicle plan to PIR | ZPP012 |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | H | ZPP01 | 1 | 2 | 1 | Complete | 2015-12-21 | 2015-12-22 |  | 2015-01-05 | 2015-01-07
PP | PP_UL_013 |  | 生产计划导入 Production planning batch input | ZPP013 |  |  | 工厂 | 张凯凯 | 曲凯 | Upload | M | H | ZPP01 | 2 | 5 | 2 | Complete | 2015-12-22 | 2015-12-24 |  | 2015-01-07
PP | PP_RP_014 |  | 生产计划查询 production planning query | ZPP014 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 2 | 1 | Complete | 2016-01-20 | 2016-01-21
PP | PP_EN_018 |  | MRP逻辑增强 安全库存按当天（第二天）需求的设定比例提高 MRP Enhancement | ZPP015 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 1 | 1 | Complete | 2015-12-24 | 2015-12-25 |  | 2016-01-13 | 2016-01-14
PP | PP_EN_020 |  | 计划订单（含计划表）增强 当订单计划手工固定或在计划表MF50 - 更改模式中被固定时，同步更新到ZTPP生产计划激活版本表，以集成生产计划导入功能与SAP标准功能 plan order enhancement | N/A |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 1 | 1 | Complete | 2015-12-25 | 2015-12-28 |  | 2016-01-13 | 2016-01-14
PP | PP_RP_015 |  | MRP结果查询 MRP result query | ZPP016 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 2 | 2 | In Develop | 2016-01-18 | 2016-01-19
PP | PP_FC_016 |  | 创建新品生产订单 create tryout production order | ZPP017 |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | M | ZPP01 | 2 | 3 | 2 | Completed by Developer | 2015-12-28 | 2015-12-30 |  | 2016-01-11 | 2016-01-14
PP | PP_RP_021 |  | 客户预测与实际库存消耗差异报表 The difference report between customer forecast and actual inventory consumption | ZPP036 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 2 | 2 | Cancel | 2016-01-25 | 2016-01-26 |  | 2016-01-26
PP | PP_RP_022 |  | 生产计划与实际生产差异报表 the difference report between Production plan and actual production | ZPP037 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 2 | 2 | Completed by Developer | 2016-01-26 | 2016-01-27 |  | 2016-01-28
PP | PP_RP_023 |  | 库存的客户需求覆盖期报表 Customer demand coverage period of stock Report | ZPP038 |  |  | 工厂 | 张凯凯 | 曲凯 | Report | L | L | ZPP01 | 1 | 2 | 2 | Completed by Developer | 2016-01-27 | 2016-01-28 |  | 2016-01-29
PP | PP_UL_025 |  | In-WFM 物料主数据清单 In-WFM material list batch input | ZPP040 |  |  | ALL | 张凯凯 | 曲凯 | Upload | L | M | ZPP01 | 1 | 1 | 1 | Completed by Developer
PP | PP_UL_026 |  | 独立需求导入 PIR Batch input | ZPP041 |  |  | 工厂 | 张凯凯 | 曲凯 | Upload | L | M | ZPP01 | 1 | 1 | 1 | In Develop
PP | PP_FC_027 |  | MRP计划订单保存(合并至PP_EN_020) Saving Planned Order after MRP | ZPP039 |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | H | ZPP01 | 1 | 1 | 1 | Cancel
PP | PP_FC_028 |  | 代开票业务销售价格导入自动扩充物料主数据 Auto extent material to billing company before sales price batch input | ZPP039 |  |  | 工厂 | 张凯凯 | 王毅 | Function | L | M | ZPP01 | 1 | 1 | 1 | Complete
PP | PP_FC_029 |  | 工艺路线批量更改 Routing mass change |  |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | L | ZPP01 | 1 | 1 | 1 | FS Wait for Approval
PP | PP_RP_030 |  | MRP结果Excel导出 MRP Result Excel Export |  |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | H | ZPP01 | 1 | 1 | 1 | FS Wait for Approval
PP | PP_RP_031 |  | 标准工时报表 TimeTicket |  |  |  | 工厂 | 张凯凯 | 曲凯 | Function | L | L | ZPP01 | 1 | 1 | 1 | Not Start
Note on B1: 实现的流程功能，一个报表等。一个索引号对应一个程序功能说明书，但可能对应多个事务代码和程序. 于支持阶段，索引号可以是变更批准号 命名规则：<模块>_<类型>_<流水号> 如：MM_UL_001 RP：Report FC：一套程序(含增强、对话、FORM、函数等） IF：interface EN: 增强；UL：上传； FR：Form； DL： Dialog
Note on F1: Yu-Bing Zhu: 在开发清单表格中维护
Note on L2: Alan: develop time L: Less Than 2 Man Days M: Between 3 to 6 Man Days H: More than 7 Man Days:

## 统计 (hidden)
行标签 | 计数项:
Completed by Developer | 10
FS Approved | 1
In Develop | 1
Not Start | 3
Unit tested by Application | 4
FS Wait for Approval | 3
总计 | 22