## 进度
| 开发项 | MES 测试项 |  |  | 2月 | [28 empty] | 3月 | [26 empty] | 4月 | [25 empty] | 5月 | [30 empty] | 6月 | [29 empty] | 7月 | [30 empty] | 8月 | [30 empty] | 9月 | [29 empty] | 10月
| 测试项 |  |  |  | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [5 empty] | W10 | [5 empty] | W11 | [5 empty] | W12 | [5 empty] | W13 | [5 empty] | W14 | [5 empty] | W15 | [5 empty] | W16 | [5 empty] | W17 | [6 empty] | W18 | [6 empty] | W19 | [6 empty] | W20 | [6 empty] | W21 | [6 empty] | W22 | [6 empty] | W23 | [6 empty] | W24 | [6 empty] | W25 | [6 empty] | W26 | [6 empty] | W27 | [6 empty] | W28 | [6 empty] | W29 | [6 empty] | W30 | [6 empty] | W31 | [6 empty] | W32 | [6 empty] | W33 | [6 empty] | W34 | [6 empty] | W35 | [6 empty] | W36 | [6 empty] | W37 | [6 empty] | W38 | [6 empty] | W39
序号 | 任务清单 | 涉及系统 | 责任人 | 备注 | time axis 2016-02-01 to 2016-10-02
[5 empty] | -151 | -150 | -149 | -148 | -147 | -146 | -145 | -144 | -143 | -142 | -141 | -140 | -139 | -138 | -137 | -136 | -135 | -134 | -133 | -132 | -131 | -130 | -129 | -128 | -127 | -126 | -125 | -124 | -123 | -122 | -121 | -120 | -119 | -118 | -116 | -115 | -114 | -113 | -112 | -111 | -109 | -108 | -107 | -106 | -105 | -104 | -102 | -101 | -100 | -99 | -98 | -97 | -95 | -94 | -93 | -92 | -91 | -90 | -88 | -87 | -86 | -85 | -84 | -83 | -81 | -80 | -79 | -78 | -77 | -76 | -74 | -73 | -72 | -71 | -70 | -69 | -67 | -66 | -65 | -64 | -63 | -62 | -61 | -60 | -59 | -58 | -57 | -56 | -55 | -54 | -53 | -52 | -51 | -50 | -49 | -48 | -47 | -46 | -45 | -44 | -43 | -42 | -41 | -40 | -39 | -38 | -37 | -36 | -35 | -34 | -33 | -32 | -31 | -30 | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
[5 empty] | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日 | 星期一 | 星期二 | 星期三 | 星期四 | 星期五 | 星期六 | 星期日
1 | 接口测试(SAP->IMES),包含所有模块。 | SAP/IMES | 杨瀛俊 | 已经做过第一轮单元测试，后期随时可以进行测试。 | bar: 星期二 to 星期六
2 | 开发IMES->SAP接口传输功能 | IMES | 吴林锋 | 贾文涛负责开发 | bar: 星期二 to 星期五
| 生产扫描模块测试 | IMES | 杨瀛俊 | 3大工艺的扫描 | bar: 星期五; 星期一
3 | 接口连通性测试(IMES->SAP)，MM模块，2个接口 | SAP/IMES | 杨瀛俊 | 库存事务接口、运单接口 | bar: 星期一
4 | 接口连通性测试(IMES->SAP)，PP模块，1个接口 | SAP/IMES | 杨瀛俊 | 生产订单报工接口。 | bar: 星期二
5 | 接口连通性测试(IMES->SAP)，PM模块，3个接口 | SAP/IMES | 杨瀛俊 | 工单接口、通知单接口、报工接口 | bar: 星期三
6 | IMES-PM模块相关功能开发 | IMES | 吴林锋 | 田志刚负责开发 | bar: 星期二 to 星期三
| 设备模块测试 | IMES | 杨瀛俊 | 通知单、维护单、维修单等功能的测试 | bar: 星期一 to 星期二
7 | 接口功能性测试(IMES->SAP)，PM模块 | SAP/IMES | 杨瀛俊 | 工单接口、通知单接口、报工接口 | bar: 星期三 to 星期四
8 | IMES-MM运单功能开发 | IMES | 吴林锋 | 罗锋负责开发 | bar: 星期五 to 星期二
| 出门证及运单功能测试 | IMES | 杨瀛俊 | 发运扫描至建运单 | bar: 星期三 to 星期四
9 | 接口功能性测试(IMES->SAP)，MM模块-运单接口 | SAP/IMES | 杨瀛俊 | bar: 星期五
| 生产订单功能测试 | IMES | 杨瀛俊 | 生产订单、生产计划报工 | bar: 星期五
10 | 接口功能性测试(IMES->SAP)，PP模块-生产订单报工接口 | SAP/IMES | 杨瀛俊 | 功能已经开发完成 | bar: 星期一
11 | IMES库存事务汇总功能开发 | IMES | 吴林锋 | 朱伟力负责开发 | bar: 星期五 to 星期二
12 | 接口功能性测试(IMES->SAP)，库存事务接口-PP | SAP/IMES | 杨瀛俊 | 生产汇报场景(生产订单汇报、生产计划汇报) | bar: 星期二
| 打磨功能测试 | IMES | 杨瀛俊 | bar: 星期一
13 | 接口功能性测试(IMES->SAP)，库存事务接口-PP | SAP/IMES | 杨瀛俊 | 返工场景(打磨、拆解) | bar: 星期三
| 手工报废 | IMES | 杨瀛俊 | bar: 星期二
14 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 库存报废 | bar: 星期四
| 手工盘点调整 | IMES | 杨瀛俊 | bar: 星期三
15 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 盘点调整(手工) | bar: 星期五
| 手工领用出库 | IMES | 杨瀛俊 | 需要与WFM一起测试 | bar: 星期四
16 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 手工领用出库(先审批后过账)，3.11开发完 | bar: 星期一
| 特殊库存转换 | IMES | 杨瀛俊 | bar: 星期五
17 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 库存状态、特殊库存转换(手工) | bar: 星期二
| 工厂内转储场景 | IMES | 杨瀛俊 | bar: 星期一
18 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 工厂间转储场景(一步法、两步法、发货、退货) | bar: 星期三
| 公司间内部交易 | IMES | 杨瀛俊 | bar: 星期二
19 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 公司间交易场景(发货、退货)--标准发货、标准收货 | bar: 星期四
| 采购退货 | IMES | 杨瀛俊 | bar: 星期三
20 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 采购场景(退货单发货)--标准发货 | bar: 星期五
| 采购收货 | IMES | 杨瀛俊 | bar: 星期四
21 | 接口功能性测试(IMES->SAP)，库存事务接口-MM | SAP/IMES | 杨瀛俊 | 采购场景(采购订单收货)--标准收货 | bar: 星期一
| 非寄售销售发货 | IMES | 杨瀛俊 | bar: 星期五
22 | 接口功能性测试(IMES->SAP)，库存事务接口-SD | SAP/IMES | 杨瀛俊 | 非寄售发货场景(发客户在途、交货确认)，3月底 | bar: 星期二 to 星期三
| 寄售发货 | IMES | 杨瀛俊 | bar: 星期一
23 | 接口功能性测试(IMES->SAP)，库存事务接口-SD | SAP/IMES | 杨瀛俊 | 寄售发货场景，3月底 | bar: 星期四
| 客户退货 | IMES | 杨瀛俊 | bar: 星期二
24 | 接口功能性测试(IMES->SAP)，库存事务接口-SD | SAP/IMES | 杨瀛俊 | 接收客户退货场景，3月底 | bar: 星期五

## schedule
| Development Item |  |  |  | 2月 | [28 empty] | 3月 | [26 empty] | 4月 | [25 empty] | 5月 | [30 empty] | 6月 | [29 empty] | 7月 | [30 empty] | 8月 | [30 empty] | 9月 | [29 empty] | 10月
| Test Item |  |  |  | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [5 empty] | W10 | [5 empty] | W11 | [5 empty] | W12 | [5 empty] | W13 | [5 empty] | W14 | [5 empty] | W15 | [5 empty] | W16 | [5 empty] | W17 | [6 empty] | W18 | [6 empty] | W19 | [6 empty] | W20 | [6 empty] | W21 | [6 empty] | W22 | [6 empty] | W23 | [6 empty] | W24 | [6 empty] | W25 | [6 empty] | W26 | [6 empty] | W27 | [6 empty] | W28 | [6 empty] | W29 | [6 empty] | W30 | [6 empty] | W31 | [6 empty] | W32 | [6 empty] | W33 | [6 empty] | W34 | [6 empty] | W35 | [6 empty] | W36 | [6 empty] | W37 | [6 empty] | W38 | [6 empty] | W39
NO. | Task List | Related System | Person in Charge | Notes | time axis 2016-02-01 to 2016-10-02
[5 empty] | -151 | -150 | -149 | -148 | -147 | -146 | -145 | -144 | -143 | -142 | -141 | -140 | -139 | -138 | -137 | -136 | -135 | -134 | -133 | -132 | -131 | -130 | -129 | -128 | -127 | -126 | -125 | -124 | -123 | -122 | -121 | -120 | -119 | -118 | -116 | -115 | -114 | -113 | -112 | -111 | -109 | -108 | -107 | -106 | -105 | -104 | -102 | -101 | -100 | -99 | -98 | -97 | -95 | -94 | -93 | -92 | -91 | -90 | -88 | -87 | -86 | -85 | -84 | -83 | -81 | -80 | -79 | -78 | -77 | -76 | -74 | -73 | -72 | -71 | -70 | -69 | -67 | -66 | -65 | -64 | -63 | -62 | -61 | -60 | -59 | -58 | -57 | -56 | -55 | -54 | -53 | -52 | -51 | -50 | -49 | -48 | -47 | -46 | -45 | -44 | -43 | -42 | -41 | -40 | -39 | -38 | -37 | -36 | -35 | -34 | -33 | -32 | -31 | -30 | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
[5 empty] | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN
1 | Interface Test（SAP->IMES），all module included | SAP/IMES | Yang Yingjun | The first unit test round has been done. Test can be conducted at any time later. | bar: TUE to SAT
2 | Develop IMES->SAP interface for transmission | IMES | Wu Linfeng | Jia Wentao takes charge of development | bar: TUE to FRI
3 | Interface connectivity test(IMES->SAP), MM, two interfaces included. | SAP/IMES | Yang Yingjun | Inventory Transaction interface, and Shipment Document interface | bar: MON
4 | Interface connectivity test(IMES->SAP), PP, one interface included. | SAP/IMES | Yang Yingjun | Production order declaration interface | bar: TUE
5 | Interface connectivity test(IMES->SAP), PM, three interfaces included. | SAP/IMES | Yang Yingjun | work order interface, notice order interface and declaration interface | bar: WED
6 | IMES-PM function module development. | IMES | Wu Linfeng | Tian Zhigang takes charge of development. | bar: TUE to WED
7 | Interface Function test(IMES->SAP), PM | SAP/IMES | Yang Yingjun | work order interface, notice order interface and declaration interface | bar: WED to THU
8 | IMES-MM shipment document function module development. | IMES | Wu Linfeng | Luo Feng takes charge of development. | bar: FRI to TUE
9 | Interface function test(IMES->SAP), MM. Shipment document interface. | SAP/IMES | Yang Yingjun | bar: FRI
10 | Interface function test(IMES->SAP), PP. Production order declaration interface. | SAP/IMES | Yang Yingjun | Function development has been done. | bar: MON
11 | IMES inventory transaction summary function development | IMES | Wu Linfeng | Zhu Weili takes charge of development. | bar: FRI to TUE
12 | Interface function test(IMES->SAP), PP. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Production Declaration scenarios include production order declaration, production plan declaration | bar: TUE
13 | Interface function test(IMES->SAP), PP. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Rework scenario(polish) | bar: WED
14 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | scrap from stock | bar: THU
15 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Physical Inventory Adjustments(Manual) | bar: FRI
16 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Consuming manually(post after approval) function development will be done on March 11 | bar: MON
17 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Inventory Status Transfer (manually) | bar: TUE
18 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Stock movement between plants(one step, two step, delivery, return) | bar: WED
19 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Cross-company Transfer(ship-ment, return, standard shipment, goods receipt) | bar: THU
20 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Purchase Scenario(deliver goods by return order)--standard delivery | bar: FRI
21 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Purchase Scenario (goods receipt according to purchase order)--standard goods receipt | bar: MON
22 | Interface function test(IMES->SAP), MM. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Non-consignment scenario(Goods for customer in transit,Delivery confirmation), function development will be done with 31 March | bar: TUE to WED
23 | Interface function test(IMES->SAP), SD. Inventory transaction interface. | SAP/IMES | Yang Yingjun | consignment scenario (delivery),function development will be done with 31 March | bar: THU
24 | Interface function test(IMES->SAP), SD. Inventory transaction interface. | SAP/IMES | Yang Yingjun | Receive return from customer. Function development will be done with 31 March | bar: FRI