## 时间进度表
时间 | 2017.3.22--2017.11.1 | CS上件自动化项目时间进度表
项目 序号 | 项 目 内 容 | 工期 | 第 一 阶 段 | 3月 | 4月 |  |  |  | 5月 |  |  |  | 6月 |  |  |  | 第 二 阶 段 | 7月 |  |  |  | 8月 |  |  |  | 9月 |  |  |  | 第 三 阶 段 | 10月 |  |  |  | 第 四 阶 段 | 11月
|  |  |  | 3.27 3.31 | 4.1 4.7 | 4.8 4.14 | 4.15 4.22 | 4.23 4.30 | 5.1 5.7 | 5.8 5.15 | 5.16 5.23 | 5.24 5.31 | 6.1 6.7 | 6.8 6.14 | 6.15 6.22 | 6.23 6.30 |  | 7.1 7.7 | 7.8 7.15 | 7.16 7.23 | 7.24 7.31 | 8.1 8.7 | 8.8 8.14 | 8.15 8.22 | 8.23 8.30 | 9.1 9.7 | 9.8 9.14 | 9.15 9.22 | 9.23 9.30 |  | 10.1 10.7 | 10.8 10.14 | 10.15 10.22 | 10.23 10.30 |  | 11.1 11.7 | 11.8 11.14 | 11.15 11.22 | 11.23 11.30
第一阶段：准备与测试
1.1 | 挂具准备 | 15天
1.2 | 注塑产品准备 | 8天
1.3 | 通用抓手方案确定 | 8天
1.4 | LAVIDA FL通用抓手制作 | 14天
1.5 | 测试用传送带方案确定 | 14天
1.6 | 通用传送带方案确定 | 25天
1.7 | 测试传送带制作 | 40天
1.9 | 项目拨款申请 | 70天
1.1 | 机器人采购 | 130天
1.11 | LAVIDA产品上件编程调试 | 12天
1.12 | 验收LAVIDA测试结果 | 5天
1.13 | TOURAN前后保抓手制作 | 18天
1.14 | TOURAN前后保测试 | 12天
1.15 | 验收Touran测试结果 | 5天
1.16 | A+前后保抓手制作 | 18天
1.17 | A+前后保测试 | 12天
1.18 | 验收A+测试结果 | 5天
1.19 | Fanuc签技术协议 | 10天
1.2 | 滑撬固定方案确定 | 30天
1.21 | 物流区域方案确定 | 25天
1.22 | AGV方案定稿 | 10天
1.23 | AGV供应商定点 | 10天
1.24 | 高位小车底盘匹配AGV | 10天
1.25 | 升降机方案交流 | 10天
1.26 | 涂装线wincc机器人 信息交互方案确定 | 25天
1.27 | 长沙产品挂具定位孔扩宽方案 | 20天
1.28 | 模具修改方案确定 | 20天
第二阶段：工厂现场施工
2.1 | 工厂挂具、检具修改 | 25天
2.2 | 机器人打地基，围栏，安全，改造等 | 14天
2.3 | 机器人进厂安装（电气和 安装到可调试状态） | 14天
2.4 | 上件区通用传送带制作 | 20天
2.5 | 滑撬固定装置安装 | 8天
2.5 | 采购定点 | 15天
2.6 | 料架和产品的匹配 | 10天
2.7 | 调试料架制作（10个） | 14天
2.8 | 批产料架制作（100个） | 60天
2.9 | AGV采购 | 40天
2.1 | AGV布置 | 10天
2.11 | AGV调试 | 14天
2.12 | 涂装线WINCC、机器人等信息交互方案实施 | 10天
2.13 | MES与AGV、高位小车等信息交互方案实施 | 25天
2.14 | 货叉与缓冲带采购 | 60天
2.15 | 2.5米传送带安装调试 | 10天
2.16 | 货叉制作与调试（供应商） | 15天
2.17 | 货叉安装调试（工厂） | 10天
2.18 | 修改产品模具（扩宽孔） | 20天
第三阶段：试运行
3.1 | 机器人参数调试 | 80h
3.2 | 物流系统运转调试 | 20天
第四阶段：正式运行
4.1 | 正式运行
计划开展
已开展，且进展顺利
已开展，存在问题但受控
已开展，进展缓慢且不受控
we are here

## Time Schedule
Time | 2017.3.22--2017.11.1 | Time Schedule
Number | Details | Work Period | 1 | Mar. | April |  |  |  | May |  |  |  | June |  |  |  | 2 | July |  |  |  | August |  |  |  | September |  |  |  | 3 | October |  |  |  | 4 | November
|  |  |  | 3.27 3.31 | 4.1 4.7 | 4.8 4.14 | 4.15 4.22 | 4.23 4.30 | 5.1 5.7 | 5.8 5.15 | 5.16 5.23 | 5.24 5.31 | 6.1 6.7 | 6.8 6.14 | 6.15 6.22 | 6.23 6.30 |  | 7.1 7.7 | 7.8 7.15 | 7.16 7.23 | 7.24 7.31 | 8.1 8.7 | 8.8 8.14 | 8.15 8.22 | 8.23 8.30 | 9.1 9.7 | 9.8 9.14 | 9.15 9.22 | 9.23 9.30 |  | 10.1 10.7 | 10.8 10.14 | 10.15 10.22 | 10.23 10.30 |  | 11.1 11.7 | 11.8 11.14 | 11.15 11.22 | 11.23 11.30
First stage：Test stage
1.1 | jigs preparing | 15days
1.2 | injection parts preparing | 8days
1.3 | confirm common grip solution | 8days
1.4 | LAVIDA FL common grip manufacture | 14days
1.5 | confirm conveyor solution for test | 14days
1.6 | common conveyor solution fix | 25days
1.7 | Test conveyor manufacture | 30days
1.9 | appropriation request | 70days
1.1 | robots purchasing | 130days
1.11 | LAVIDA FL parts program test | 12days
1.12 | check result of LAVIDA FL parts | 5days
1.13 | TOURAN parts grip manufacture | 18days
1.14 | TOURAN parts test | 12days
1.15 | check result of touran parts | 5days
1.16 | A+ parts grip manufacture | 18days
1.17 | A+ parts test | 12days
1.18 | check result of A+ parts | 5days
1.19 | technology agreement with fanuc | 10days
1.2 | skid fix solution | 30days
1.21 | logistics area solution fix | 25days
1.22 | AGV solution fix | 10days
1.23 | AGV supplier fix | 10days
1.24 | high rack match the AGV | 10days
1.25 | elevator solution | 10days
1.26 | wincc,robot information exchange | 25days
1.27 | Jigs location hole solution | 20days
1.28 | Mold modification solution | 20days
Second stage：plant construction
2.1 | jigs modification | 25days
2.2 | lay the foundations for robots | 14days
2.3 | robots installation in plants | 14days
2.4 | Common conveyor manufacture on loading area | 20days
2.5 | skid fix equipment installation | 8days
2.6 | rack and the parts matching | 10days
2.7 | high rack manufacture for testing(10) | 14days
2.8 | high rack manufacture(100) | 60days
2.9 | AGV purchasing | 40days
2.1 | AGV arrangement | 10days
2.11 | AGV debugging | 14days
2.12 | wincc,AGV,robot information exchange implement | 10days
2.13 | MES,AGV,high shelf information exchange implement | 25days
2.14 | folk+conveyor purchasing | 60days
2.15 | 2.5 meter conveyor installation and test | 10days
2.16 | the folk manufacture and test in supplier factory | 15days
2.17 | the folk installation and test in plant | 10days
2.18 | Mold modification implement | 20days
Third stage：trial in plant
3.1 | robot parameter debugging | 80h
3.2 | logistics system testing | 20days
Last stage：formally run
4.1 | formally run
we are here

## 问题清单PDCA
RAISED提出
|  | 机器人自动上下件 PDCA |  |  |  |  | STARTED启动 | x
[7 empty] | ANALYSIS(P)分析决策 | x | x
[7 empty] | IMPLEMENTED(D)实施 | x | x | x
[7 empty] | VERIFIED (C)验证 | x | x | x | x
|  | Date : |  | 2017-05-16 |  |  | CLOSED (A)关闭 | x | x | x | x | x
序号 | 区域模块 | Problems identified / Actions 问题描述 | 主要负责人 | Responsible 具体负责人 | 工厂对口人员 | Issue date 提出日期 | Due date 计划完成日期 | Status 状态 |  |  |  |  | Comments / Further Actions 备注
1 | 挂具 | 塑料定位销使用后的变形情况。更改定位块尺寸，使配合更紧 | 黄宇锋 | 黄宇锋 | 姜泰幅 | 2017.3.22 | 2017.3.29 | x | x | x | x | x | 塑料定位销自身不发生变形。尺寸已输出
2 |  | 确认LAVIDA前保高位挂具是否共用 |  | 姜泰幅 | 姜泰幅 | 2017.3.22 | 2017.3.24 | x | x | x | x | x | 前保共用
3 |  | 制作new LAVIDA FL 10前6后挂具 |  | 姜泰幅 | 姜泰幅 | 2017.3.22 | 2017.4.10 | x | x | x | x | x | 已完成挂具制作
4 |  | 设计挂具定位铁片，输出尺寸图纸 |  | 黄宇锋 | 姜泰幅 | 2017.3.22 | 2017.3.29 | x | x | x | x | x | 已输出，且挂具铁片制作完成
5 |  | 确认定位块加工工艺，加工图纸尺寸 |  | 姜泰幅 | 姜泰幅 | 2017.3.22 | 2017.3.24 | x | x | x | x | x | 已完成确认
6 |  | 批产项目定位孔修改方案 |  | 姜泰幅 |  | 2017.4.13 | 2017.4.30 | x | x | x | x | x
7 |  | 朗逸前后保模具修改 |  | 姜泰幅 |  | 2017.4.28 | 2017.5.30 | x | x | x
8 |  | 途安前后保模具修改 |  | 姜泰幅 |  | 2017.5.16 | 2017.6.15 | x
9 |  | 新项目定位孔尺寸加大评估方案输出，工程反馈设计科新方案是否存在风险 |  | 朱玉满\党一届 |  | 2017.4.13 | 2017.5.21 | x | x
10 |  | 塑料定位销结构改进方案输出，并完成供应商交流、报价 |  | 黄宇锋 |  | 2017.4.13 | 2017.4.21 | x | x | x | x | x
11 |  | 塑料定位销新模具制作 |  | 黄宇锋 |  | 2017.5.15 | 2017.6.15 | x
12 |  | 所有长沙产品数模发送物流团队 |  | 黄宇锋 |  | 2017.4.14 | 2017.4.14 | x | x | x | x | x | 已发送韶峋
13 | 机械装置 （抓手&传送带） | 输出所有产品数模 | 顾荣荣 | 顾荣荣 | 姜泰幅 | 2017.3.22 | 2017.3.28 | x | x | x | x | x | 优先LAVIDA前后保
14 |  | 发送LAVIDA前、后保注塑件。 |  | 卓铁武 |  | 2017.3.22 | 2017.3.30 | x | x | x | x | x | 已完成
15 |  | LAVIDA前保脱钩盖板一箱发给FANUC |  | 卓铁武 |  | 2017.3.22 | 2017.3.31 | x | x | x | x | x | 完成
16 |  | 确定测试用传送带方案 |  | 顾荣荣 |  | 2017.4.10 | 2017.4.21 | x | x | x | x
17 |  | 测试用传送带制作完成 |  | 顾荣荣 |  | 2017.4.14 | 2017.6.25 | x | x
18 |  | 模拟传送带修改以适应长沙产品New LAVIDA fl |  | 顾荣荣 |  | 2017.4.28 | 2017.5.7 | x | x
19 |  | 通用传送带方案，适应不同产品定位。工厂自制 |  | 姜泰福 |  | 2017.3.22 | 2017.5.8 | x | x | x
20 |  | 与供应商沟通回复共用抓手方案完成时间 |  | 顾荣荣 |  | 2017.3.22 | 2017.3.30 | x | x | x | x | x | 原定4月14日完成，现推迟到4月18日
21 |  | 完成朗逸前后保共用抓手方案 |  | 顾荣荣 | 顾荣荣 | 2017.3.26 | 2017.4.17 | x | x | x | x
22 |  | 完成朗逸前后保共用抓手制作 |  | 顾荣荣 |  | 2017.4.17 | 2017.5.7 | x | x | x | x
23 |  | 完成途安前后保共用抓手方案 |  | 顾荣荣 | 顾荣荣 | 2017.5.16 |  | x |  |  |  |  | 5月26日前确定朗逸抓手使用效果，再进行设计
24 |  | 完成途安前后保共用抓手制作 |  | 顾荣荣 |  | 2017.5.16 |  | x
25 |  | 通用抓手技术协议初稿 |  | 顾荣荣 | 顾荣荣 | 2017.5.16 | 2017.6.15 | x
26 |  | 柔性传送带技术协议初稿 |  | 顾荣荣 |  | 2017.5.16 | 2017.6.15 | x
27 | 信息交互 | MES系统拉动产品自动送达 确认MES系统功能要求 | 姚志军 | 姚志军 | 澎湃 | 2017.3.22 | 2017.4.6 | x | x | x | x | x | 已制作MES系统功能图
28 |  | 滑撬定位装置，考虑防止滑撬翻转的结构。立柱固定，防止震动过大 与艾森曼交流确定改造方案. 细化方案输出 |  | 姚志军 |  | 2017.3.22 | 2017.6.2 | x | x | x |  |  | 已有初步方案
29 |  | wincc与机器人、传送带的联动 艾森曼、fanuc、agv供应商交流，确定初步方案 |  | 姚志军 | 澎湃 | 2017.3.22 | 2017.3.29 | x | x | x | x | x
30 |  | 输出wincc与机器人、传送带、抓手的联动方案 WINCC与机器人传送信息的形式、方法 |  | 姚志军 |  | 2017.4.14 | 2017.6.2 | x | x
31 |  | AGV、WINCC、升降机、机器人等设备通讯方式汇总发出 |  | 姚志军 | 澎湃 | 2017.4.11 | 2017.4.19 | x | x | x | x | x
32 |  | 确定MES与wincc信息交互方式（完成与供应商交流） |  | 姚志军 |  | 2017.4.28 | 2017.4.28 | x | x | x | x | x
33 |  | 确定MES与升降机信息交互方式（完成与供应商交流） |  | 姚志军 |  | 2017.4.28 | 2017.5.12 | x | x | x | x
34 |  | 确定MES与条码枪信息交互方式（完成与供应商交流） |  | 姚志军 |  | 2017.4.28 | 2017.5.30 | x
35 |  | 艾森曼技术协议初稿 |  | 姚志军 |  | 2017.5.16 | 2017.6.15 | x
36 | 物流 | 物流方案输入信息收集确认（注塑件分产品库存水平需求，小件的翻箱点） | 吴伟 | 彭湃 |  | 2017.4.11 | 2017.5.4 | x | x | x | x | x
37 |  | 上件项目物流方案初稿输出（含脱钩盖板安装地点） |  | 吴伟 | 澎湃 | 2017.4.13 | 2017.4.28 | x | x | x | x
38 |  | 上件项目物流方案细化输出，最终方案输出 |  | 吴伟 |  | 2017.4.28 | 2017.6.1 | x | x | x
39 |  | 利用产品数模，完成料架与产品匹配（四个小件产品） |  | 张韶峋 |  | 2017.4.13 | 2017.5.15 | x | x | x | x | x
40 |  | 返喷件深色和浅色产品预检测，输出颜色信号 输出返喷件运作流程 |  | 彭湃 |  | 2017.3.22 | 2017.4.28 | x | x | x | x | x
41 |  | 根据AGV运转节拍等信息确定wincc一次性至少传送给MES系统多少车信息数据？以及何时执行下一次传送命令？ |  | 吴伟 |  | 2017.4.11 | 2017.5.26 | x | x |  |  |  | 与工厂、艾森曼交流
42 |  | 确定MES与AGV信息交互方式（完成与供应商交流） |  | 吴伟 |  | 2017.4.28 | 2017.4.28 | x | x | x | x | x
43 |  | MES系统开发时间计划输出 |  | 金凌 |  | 2017.4.14 | 2017.5.26 | x
44 |  | 机器人上件安装位置确认 |  | 吴伟 |  | 2017.4.12 | 2017.6.1 | x
45 |  | 产品料架设计 |  | 吴伟 | 澎湃 | 2017.4.13 |  | x
46 |  | AGV技术协议 |  | 吴伟 |  | 2017.5.16 | 2017.6.15 | x
47 | 机器人 | 上件是否到位检测识别、报警功能 | 姚志军 | 王萌珏 | 姜泰幅 | 2017.3.22 | 2017.4.17 | x |  |  |  |  | 暂时没有方案
48 |  | 放入产品前增加一次拍照，fanuc测试方案 |  | 王萌珏 |  | 2017.3.22 | 2017.5.23 | x | x |  |  |  | 正在开展
49 |  | 脱钩盖板抓手方案确定 |  | 姜泰福 |  | 2017.5.16 | 2017.5.26 | x
50 |  | 定位销偏斜检测、矫正方法 确定极限阈值范围 |  | 王萌珏 | 姜泰幅 | 2017.3.22 |  | x |  |  |  |  | 上件测试开始时再确定完成时间
51 |  | 根据通讯总线确定机器人类型 |  | 姚志军 | 姜泰幅 | 2017.3.22 | 2017.3.30 | x | x | x | x | x
52 |  | FANUC机器人技术协议初稿 |  | 姚志军 |  | 2017.5.16 |  | x
53 | 其他 | 升降机初步方案，第二轮方案输出 |  | 顾海明 | 顾海明 | 2017.4.28 | 2017.5.20 | x | x
54 |  | 升降机技术协议初稿 |  | 顾海明 |  | 2017.5.16 | 2017.6.15 | x
55 |  | 反馈时间进度表中事项、工期、节点是否需要更新 |  | 姚志军、顾荣荣、吴伟 |  | 2017.4.14 | 2017.4.21 | x | x | x | x | x
56 |  | 拨款申请审批 |  | 彭湃 |  | 2017.4.28 | 2017.6.20 | x
57 |  | 机器人放置区域周边安全问题 |  |  | 胡烟平 |  |  | x
1900-01-07
|  |  |  | 计划关闭数 |  | 实际关闭数 | 关闭率
[9 empty] | 38 | 31 | 27 | 22
[9 empty] | 16 | 9 | 5 | 22

## Sheet3
| 升降机 | 90 | 3
| AGV | 150 | 5
| 料架 | 100
学生综合征
14.7mm
7.8mm
60mm
16mm